## Sheet1
List of NCAP Phase-I works
08.02.2022
Sr. no. | Zone | Constituency | Sub Zone | Ward no. | Name of Councillor | Name of Work | Estimate Cost (in lacs) | Estimate approved by F&CC/Technical Advisory committee vide Resolution No. & date | Amended E/Cost (Lacs) | No. of Tenders Received | OAS (%) | Saving (Rs.) | Tender Cost (in lacs) | Work Oder no./dt. | Time lImit | Date of Completion | Agency | Physical Progress (%age) | Financial Progress Progress (Lacs) | Remarks
1 | A | North | A3 | 2 | Sh. Gurmail Singh | Rejuvenation of Main Bahadur Ke Road by Laying BM & SDBC | 112.06 | ` | 112.06 | 1 | 4% | 448240 | 107.57 | 49/LOA dt.30-09-2021 | 4 | 31.01.2022 | S.S Singla Contractor | 15% | 0 | R/G work completed Bitumen work will be done after Winter Season
2 | A | Central & North | A2 | 54 & 64 | Smt. Surinder Kaur Manna w.no.54 & Sh. Rakesh Prasher w.no.64 | Rejuvenation of Main Field Ganj Road & Shahpur Road , Ludhiana | 100 | Reso No. 4022 Dt 15-03-2021 | 114.21 | 2 | -9.01% | 1029032 | 103.92 | 55/EEA dt. 14-10-2021 | 4 | 31.01.2022 | APEX BUILDERS | 20% | 8 | R/G work completed Bitumen work will be done after Winter Season
3 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Const of Road by laying 30mm thick BC on main RK Road W No.20 | 88.15 | 3887, Dt 15.03.2021 | 96.86 | 4 | 4.65 | 450399 | 92.36 | 52 01.10.2021 | 4 | 31.01.2022 | Sh SS Singla Contractor | 75% | 0 | Work is in Progress
4 | C | _ | _ | _ | _ | S/O Ready Mix road repair Bituminous material for central store MC Ludhiana | 95.58 | 4726, 05.07.2021 | 95.58 | 1 | 1.5 | 143370 | 94.15 | 14 02.08.2021 | 12 | 01.08.20222 | Sh Krishan Road Products | 25% | 23.44 | Work is in Progress
5 | D | West | D4 | 65 | Smt. Poonam Malhotra | Laying SDBC on Sham Nagar main road from Bus Stand to Jagraon Bridge in ward no 65 | 93.74 | approval in anticipation W.Mayor 20-08-2021 WCC= 01-08-2021 CE-2021/33577 dt 20-08-2021 | 104.12 | 1 | -6.83 | 711140 | 97.01 | 54/EED 06-09-2021 | 3 | 16.12.2021 | M/s Somaya Infra | 100% | 85.25 | Work Completed
6 | D | West | D3 | 67 | Smt. Mamta Ashu | Rejuvenation of Road from Hero Bakery Chowk to Railway Crossing. | 65.55 | 4338 05-07-2021 | 60.17 | 3 | -6 | 361020 | 56.56 | 39/EED 09-08-2021 | 4 | 09.11.2021 | M/s Ganpati Infra | 90% | 42.56 | Work is in Progress
7 | D | Atam Nagar & West | D2 | 46, 48, 69 | 1. Sh. Harbhajan Singh Dang 2. Sh. Palvinder Singh Lapran 3. Smt. Kulwnder Kaur | Laying SDBC on main Ishmeet Singh Road, Dana Mandi Railway crossing to Dugri bridge and up to Pakhowal Road (ward no. 46-48,69) | 240 | 3920 15-03-2021 | 286.22 | 2 | -6.1 | 1745942 | 268.76 | 55/EED 06-10-2021 | 3 | 06.01.2022 | M/s S.S Singla Contractor | 40% | 0 | Work is in Progress
8 | D | North | D1 | 83 | Smt. Indu Thapar | Reconditioning of Brindavan road to Damoria Bridge via Kailash Chowk main road | 144.36 | 3902 15-03-2021 | 161.48 | 1 | -13.3 | 2147684 | 140 | 61/EED 12-10-2021 | 6 | 11.04.2021 | M/s NKC Construction Pvt. Ltd. | 0% | 0 | Not Started
9 | D | Gen | D | Gen | - | Detailed estimate for creation of green buffers along road sides in Ludhiana | 95.88 | - | 94.04 | 2 | -6.86 | 645114 | 87.59 | 103 Dt 12.10.2021 | 6 | 11.04.2021 | M/s Actve Plantation | 15% | 0 | Preguard fabrication work in progress
10 | D | Gen | D | Gen | - | Detailed estimate for greening of parks, open areas, community places, schools & housing societies in Ludhiana | 95.38 | - | 91.89 | 2 | -6.86 | 630365 | 85.59 | 102 Dt 12.10.2021 | 6 | 11.04.2021 | M/s Actve Plantation | 15% | 0 | Preguard fabrication work in progress
11 | Workshop | Gen | O&M | __ | __ | 16 nos. water sprinklers. Fabrication of 16 nos. S.S. Water Tanker Trolley of capacity 5000 ltr. & size 12'X5'x4' to be mounted on trolley made out of 200'x100mm M.S. Joist with necessary pully/ toeing arrangement. | 38 | F&CC Resolution No. 4022 dated 15-03-2021 | 45.69 | 1 | 9.17 | 4.19 | 41.5 | Work Order No. 67/G33 dated 01-10-2021. | 3 | 31.12.2021 | Kakar Associates | 20% | 0 | Work is in Progress
12 | Workshop | Gen | O&M | __ | __ | Supply of chassis and fabrication of 1 nos. of Fire Tender LPT 1918 BS-VI for Dump Site. | 93 | F&CC Resolution No. 4022 dated 15-03-2021 | 61.98 | 1 | 8.79 | __ | 56.53 | __ | 2 | 31.12.2021 | M/s Khalsa Motor Fab. | 20% | 0 | Work is in Progress
13 | Workshop | Gen | O&M | __ | __ | Providing and Installation of anti smog guns upto 100 Mts road | 88 | F&CC Resolution No. 4022 dated 15-03-2021 | 88 | __ | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Financial bid opened dt 07.01.2022.
14 | Workshop | Gen | O&M | __ | __ | Providing and Installation of E Rickshaw Mounted Anti Smog Guns | 39 | F&CC Resolution No. 4022 dated 15-03-2021 | 39 | __ | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Financial bid opened dt 07.01.2022.
15 | Workshop | Gen | O&M | __ | __ | Design, Fabrication, Supply, Commissioning, testing and handing over of 04 Nos. sweeping Machines to Municipal corporation Ludhiana with operation and maintenance for 3 years | 508 | F&CC Resolution No. 4022 dated 15-03-2021 | 454.34 | 1 | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Case is under process.
16 | Workshop | Gen | O&M | __ | __ | Supply, Operation and Maintenance of 4 Nos. E Road Sweeping Machines for Municipal Corporation of Ludhiana | 588.8 | F&CC Resolution No. 4022 dated 15-03-2021 | 588.8 | __ | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Participated agencies have been asked to give clerifications as directed by Chief Engineer,
[7 empty] | 2485.5 |  | 2494.44 |  |  |  | 1231.54 | [5 empty] | 159.25