## Sheet1
List of NCAP Phase-II works
08.02.2022
Sr. no. | Zone | Constituency | Sub Zone | Ward no. | Name of Councillor | Name of Work | Estimate Cost (in lacs) | Estimate approved by F&CC/Technical Advisory committee vide Resolution No. & date | Amended E/Cost (Lacs) | No. of Tenders Received | OAS (%) | Saving (Rs.) | Tender Cost (in lacs) | Work Oder no./dt. | Time lImit | Targeted date to achieve 100% completion | Agency | Physical Progress (%age) | Financial Progress Progress (Lacs) | Remarks
1 | A | North | A4 | 87 | Smt. Kulwant Kaur | Developement of Sabzi Mandi Park near Budha Nallah adjoining Petrol Pump. | 99.38 | 4454 dt.05-07-2021 | 89.03 | 5 | 21% | 1869630 | 70.33 | 47/EEA dt.30-09-2021 | 4 | 31.03.2022 | M/s Surya Construction | 35% | 22.06 | Work in progress
2 | A | North | A4 | 84 | Sh. Surinder Atwal | Developement of 2 nos. Park near Budha Nallah adjoining Bhai Manna Singh Nagar. | 99.26 | 4454 dt.05-07-2021 | 96.21 | 4 | 21.21% | 2040614 | 75.8 | 46/EEA dt.30-09-2021 | 4 | 31.01.2022 | M/s Apex Developers | 30% | 19.86 | Work in progress
3 | A | North | A4 | 85 | Smt. Sunita Rani | Developement of 3 nos. Green Belt/Park opposite Chand Cinema including repair of Boundary Walls, Grills, Footpath & Painting etc. | 98.93 | 4454 dt.05-07-2021 | 93.21 | 4 | 20.02% | 1866064 | 74.54 | 48/EEA dt.30-09-2021 | 4 | 31.01.2022 | M/s Ayuchika & Daughters | 30% | 21.13 | Work in progress
4 | A | North | Gen. | Gen. | Gen. | Rejuvenation of Elevated Road from Jagraon Bridge to Chand Cinema by laying Mastic Asphalt. | 341.22 | Reso No. 4454 Dt 05-07-2021 | 316.67 | 1 | -10.56% | 3344035 | 283.23 | 123/EEA dt.06-12-2021 | 6 | 2022-06-05 | NKC CONSTRUCTIONS PVT. LTD. | 0 | 0 | Work will be started after winter Season
5 | A | North | Gen. | Gen. | Gen. | Development of Green Pockets/Planters below Elevated Road from Jagron Bridge to Budha Nallah. | 49.05 | Reso No. 4454 Dt 05-07-2021 | 47.76 | 1 | 22% above |  | 58.26 | 98/EEA dt 06-12-2021 | 6 | 2022-06-05 | Navyug Company | 20% | 15 | Work in progress
6 | B | East | B3 | 15 | Smt Kanchan Malhotra | Const. of RCC Road by laying RMC (M-30) from Tibba road via STP Plant on Kakka Dhaula Main Road W No.15 | 112.23 | 4454, Dt 05.07.2021 | 108.73 | 4 | 22.66 | 2463822 | 84.09 | 49, Dt 01.10.2021 | 6 | 31.03.2022 | M/s Ashok Kumar Sobti | 30% | 30 | Work is in Progress
7 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Repair & Maintenance of Guru Nanak Park opposite Councillor House near Cheema Chowk | 68.48 | 4454, Dt 05.07.2021 | 63.84 | 4 | 22.6 | 1442784 | 49.41 | 50, Dt 01.10.2021 | 5 | 28.02.2022 | Sh Ram Parkash Kakkar | 35% | 0 | Work is in Progress
8 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Recarpeting of main Shingar Cinema Road from Samrala Chowk to Shagun Palace | 77.96 | 3886, Dt 15.03.2021 | 91.2 | 3 | 4.5 | 410400 | 87.1 | 51, Dt 01.10.2021 | 6 | 31.03.2022 | M/s Apex Builders | 85% | 87.09 | Work is in Progress
9 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Green Belt opposite Arun Gas near Cheema Chowk | 29.5 | 4454, Dt 05.07.2021 | 29.5 | 2 | 21.29 | 628055 | 23.22 | 53, Dt 06.10.2021 | 3 | 05.01.2022 | M/s T&G Const Co. | 90% | 21.09 | Work is in Progress
10 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Repair & Maintenance of Green Belt backside Shani Dev mandir | 14.78 | 4454, Dt 05.07.2021 | 14.78 | 1 | 13.89 | 205295 | 12.73 | 54, Dt 06.10.2021 | 3 | 05.01.2022 | M/s Teg Builders | 95% | 11.9 | Work is in Progress
11 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Repair & Maintenance of Green Belt oppsite PNB Bank near Cheema Chowk | 20.94 | 4454, Dt 05.07.2021 | 20.94 | 1 | 13.89 | 290857 | 18.03 | 55, Dt 06.10.2021 | 3 | 05.01.2022 | M/s Teg Builders | 90% | 11.52 | Work is in Progress
12 | B | Central | B1 | 20 | Sh Ravneet Ghayal | Recarpeting of Road from Cheema Chowk to Issa Nagari Pully | 84.17 | 3888, Dt 15.03.2021 | 95.75 | 3 | 21.68 | 2075860 | 74.99 | 56, Dt 08.10.2021 | 6 | 08.04.2022 | Sh Hitesh Aggarwal | 95% | 91 | Work is in Progress
13 | B | East | B4 | 21 | Smt Kitty Uppal | Construction of Green Belt along G.T. Road near Tubewell Moti nagar,Block-A W. no. 21 | 47.7 | 4454, Dt 05.07.2021 | 47.7 | 1 | 1.5 | 12402 | 46.98 | 57, Dt 03.12.2021 | 3 | 02.03.2022 | Sh Varinder Singh Govt Contractor | 10% | 0 | Work is in Progress
14 | B | East | B3 | 14 | Sh Kuldeep Jhanda | Const of pullies around Budha Nallah | 400 | 4454, Dt 05.07.2021 | 407.93 |  |  |  |  | _ |  |  |  | _ | 0 | Tendering Reinvited dt 03.01.2022
15 | C | South , Central | C | 50,51 | Sh. Swaranjit Singh Chahal & Smt Amrit Kaur Dico | Construction of Footpaths in green belt along old GT road from Military camp up to jagraon bridge up ramp. | 60.71 | 4454, dt 05.07.21 | 70.77 | 4 | -26.68 | 18.89 | 51.88 | 235/EE/C dt 07.12.2021 | 5 | 06.05.2022 | Aglow builders | 25% | 0 | Work is in Progress
16 | C | South , Central | C | 50,51 | Sh. Swaranjit Singh Chahal & Smt Amrit Kaur Dico | Construction of Footpaths in green belt along old GT road from jagraon bridge down ramp towards sherpur chowk. | 77.01 | 4454, dt 05.07.21 | 88.75 | 5 | -24.99 | 22.18 | 66.57 | 229 Dt 02.11.2021 | 5 | 01.04.2022 | Apex developers (50%) & Binny Contractor (50%) | 45% | 13.38 | Work is in Progress
17 | C | South , Central | C | 40 | Sh.Arjun Singh Cheema | Construction of boundary wall , Footpath and painting of park old GT road near Achaar shop ward no. 40. | 33.01 | 4454, dt 05.07.21 | 28.8 | 2 | -24.99 | 7.2 | 21.6 | 225/EEC, dt 14.10.2021 | 2 | 13.12.2021 | Binny Contractor | 90% | 12.51 | Work is in Progress
18 | C | South , Central | C | 50,51 | Sh. Swaranjit Singh Chahal & Smt Amrit Kaur Dico | P/F of missing MS grills in green belts and missing RCC grills in central verge from jagraon bridge upto sherpur chowk both sides. | 29.3 | 4454, dt 05.07.21 | 22.11 | 1 | -1.2 | 0.3 | 21.81 | 230, Dt 02.11.2021 | 2 | 01.01.2022 | Parveen Sehgal | 70% | 0 | Work is in Progress
19 | C | South , Central | C | 50,51 | Sh. Swaranjit Singh Chahal & Smt Amrit Kaur Dico | Development of parks , Green belt and Recarpeting of road on old GT road from Foot of jagraon bridge upto sherpur chowk. | 265.27 | 4454, dt 05.07.21 | 392.91 | 2 | -19.68 | 77,32,468 | 315.58 | 227, dt 29.10.2021 | 6 | 28.04.2022 | M/S Apex Builders | 35% | 57.5 | Work heldup due to winter season
20 | D | West | D4 | 65 | Smt. Poonam Malhotra | Reconditioning of Ramp of Jagraon Bridge | 58.96 | 4454 05-07-2021 | 58.96 | 58.96 | 2 | -21.68 | 1278253 | 46.18 | 57/EED 06-10-2021 |  | M/s Hitesh Aggarwal Cont. | 95% | 35.23 | Work in Progress
21 | D | West | D3 | 74 | Sh. Pankaj Sharma | Construction of Green Belt along Sua Road from Sidhwan Canal to Barewal Octroi Road | 142.15 | 4454 05-07-2021 | 144.7 | 144.7 | 1 | (-)1.00 | 114700 | 113.55 | 159/EED 6-12-2021 |  | M/s Parveen Sehgal Cont. | 30% | 30.2 | Work in Progress
22 | D | Atam Nagar | D2 | 44 | Sh.Karkarandeep Singh Vaid | Construction of park adjoining Raghunath Enclave along Canal, ward no. 74. | 134.2 | 4454 05-07-2021 | 116.89 | 116.89 | 1 | -2.89 | 337812 | 113.51 | 59/EED 12-10-2021 |  | M/s T&G Construction Co. | 5% | 0 | Work stopped due to land dispute
23 | D | West | D3 | 74 | Sh. Pankaj Sharma | Construction of Environmental friendly park in Barewal Village, ward no. 74. | 240.09 | 4454 05-07-2021 | 206.41 | 206.41 | 1 | -0.5 | 103205 | 205.38 | 60/EED 12-10-2021 |  | M/s Anil Kumar & Sons | 25% | 0 | Work in Progress
24 | D | Atam Nagar | D2 | 49 | Smt. Rajinder Kaur | Development of Green Belt along Sidhwan Canal Dugri Road to Dhuri Railway Lines, Ludhiana | 330.01 | 4454 05-07-2021 | 318.05 | 318.05 | 1 | (-)1.00 | 318050 | 314.49 | 172/EED 06-12-2021 |  | M/s Asis Builders | 45% | 50.25 | Work in Progress
[6 empty] | Total | 2914.31 |  | 2971.6 |  |  |  | 2153456.15 |  |  |  |  | ` | 529.72