## Sheet1
List of Solid Waste Management Phase-I Works
O&M Cell & Workshop
08.02.2022
Sr. No. | Constituency | Sub Zone | New W No. | Name of Councillor | Name of Work | E/Cost (Lacs) | Estimate approved by F&CC vide Resolution No. & date | Amended E/Cost (Lacs) | No. of Tenders Received | OAS (%) | Saving (Rs.) | T Cost (In Lacs) | Work Order No. & Date | Time lImit | Targeted date to achieve 100% completion | Agency | Physical Progress | Financial Progress Progress (Lacs) | Remarks
1 | __ | O&M | __ | __ | Purchase of Safety Equipment for Sewerman in Municipal Corporation Ludhiana. | 598.43 | F&CC Resolution No. 4023 dated 15-03-2021 | 245.52 | 2 | 12.41 | 30.45 | 215.07 | 82/G33 01-11-2021. | 1 month | 30-11-2021 | Technosafe Solutions | 80% | 112.2 | Work in progress
2 | __ | O&M | __ | __ | Purchase of Tippers (14 cum) | 71.11 | F&CC Resolution No. 4023 dated 15-03-2021 | 71.11 | 6 | 3.33 | 2.37 | 68.74 | 66/G33 01-10-2021. | 45 days | 15-11-2021 | ARP Motors Private Limited | __ | 0 | Work order issued.
3 | __ | O&M | __ | __ | Tata Ace Tippers | 225 | F&CC Resolution No. 4023 dated 15-03-2021 | 158 | 18 | 21.32 | 33.68 | 124.32 | 65/G33 01-10-2021. | 45 days | 15-11-2021 | Guru Kripa Footwear | __ | 0 | Work order issued.
4 | __ | O&M | __ | __ | Installation of Sludge Submersibe Pump make JASCO, KSB, ABS, XYLEM, Grunfos, Ebara & Sulzer (including accessories) with control panel extra submersible cable. | 161.18 | F&CC Resolution No. 4023 dated 15-03-2021 | 79.09 | 2 | 24.14 | 19.09 | 60 | 80/G33 01-11-2021. | 4 months | 28-02-2022 | HM Electro Mac Ltd. | __ | 0 | Work order issued.
5 | __ | O&M | __ | __ | Harvesters/ Shredder | 19.03 | F&CC Resolution No. 4023 dated 15-03-2021 | 19.03 | 1 | 0.16 | 0.03 | 19 | 79/G33 01-11-2021. | 45 days | 15-11-2021 | Trade link Engg. Service | 100% | 0 | Work Comleted
6 | East | O&M | 12,15 & 16 | __ | Prov. & Installtion of 25 HP (200 mtr) Straight Bore Tubewell at Puneet Nagar, Simranjeet Nagar & Preet Nagar in Ward No- 12, 15 & 16. | 33.06 | F&CC Resolution No. 4566 dated 05-07-2021 | 31.62 | 3 | 6.8 | 2.15 | 29.47 | 64/G33 30-09-2021. | 4 months | 31-01-2022 | The Mohi Co-op L&C Society Ltd. | 100% | 29.18 | Work completed
7 | East | O&M | 15 | Smt. Kanchan Malhotra | P/L of 4” DIK-7 water supply line at Puneet Nagar (Nr. Dump Slum Area) in W. No. 15. | 97.55 | F&CC Resolution No. 4566 dated 05-07-2021 | 95.64 | 1 | 3.29 | 3.15 | 92.49 | 76/G33 01-11-2021. | 2 months | 31-12-2021 | Bedi Pump Store | 95% | 57.94 | Work in progress
8 | East | O&M | 2,4,12,13,14,15,16,17 & 23 | __ | P/L of 4” DIK-7 water supply line in different areas at W. No. 2,4,12,13,14,15,16,17 & 23. | 99.67 | F&CC Resolution No. 4566 dated 05-07-2021 | 98 | 1 | 3.29 | 3.222 | 94.78 | 75/G33 01-11-2021. | 2 months | 31-12-2021 | Bedi Pump Store | 95% | 60.45 | Work in progress
9 | __ | O&M | __ | __ | Compartmentalized E-Rehras | 410.5 | F&CC Resolution No. 4023 dated 15-03-2021 | 410.5 | 11 | 0.5 | 2.5 | 408 | 126/G33 30-12-2021. | 1.5 month | 2022-02-14 | Republic Motors | 0% | 0 | Work order issued.
10 | __ | O&M | __ | __ | Garbage Picking Trolleys | 99.26 | F&CC Resolution No. 4023 dated 15-03-2021 | 99.26 | 4 | 17.18 | 17.06 | 82.2 | __ | __ | __ | Kakkar Associates | __ | 0 | File sent to F&CC for approval of allottement
11 | __ | O&M | __ | __ | Purchase of Backhoe Loader with 0.3 cum. | 282 | F&CC Resolution No. 4023 dated 15-03-2021 | 242 | 2 | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Case under process
12 | __ | O&M | __ | __ | Purchase of Tractors | 290.47 | F&CC Resolution No. 4023 dated 15-03-2021 | 231.93 | 4 | __ | __ | __ | __ | __ | __ | __ | __ | 0 | Case under process
13 | __ | O&M | __ | __ | Purchase of Compactors and Purchase of Hook Loaders for compactors. | 400 | F&CC Resolution No. 4023 dated 15-03-2021 | 372.5 | 2 | 21.65 | 80.65 |  | __ | __ | __ | Pyara Singh & Sons | __ | 0 | Case under process
[5 empty] | Total | 2787.26 |  | 2154.2 |  |  |  | 1194.07 | [5 empty] | 259.77