## Sheet1
Main Summary (Project-wise)
[22 empty] | 08.02.2022 | [5 empty] | Detail of works
Sr No. | Description | No. of Works |  |  |  |  | Amended E/Cost Vetted by CE | [5 empty] | E/Cost |  |  |  |  | Amended E/Cost |  |  |  |  | Financial Progress (Lacs) |  |  |  |  | Started |  |  |  |  | Not Started |  |  |  |  | Completed
|  | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | [6 empty] | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | NCAP-I | NCAP-II | SWM-I | SWM-II | Total | NCAP-I | NCAP-II | SWM-I | SWM-II | Total
1 | Work order Issued | 12 | 23 | 9 | 12 | 56 | [6 empty] | 1261.7 | 2514.31 | 1715.53 | 1890.91 | 7382.45 | 1324.3 | 2563.67 | 1208.51 | 1802.3 | 6898.78 | 159.25 | 529.72 | 259.77 | 500.22 | 1448.96 | 10 | 20 | 3 | 9 | 42 | 1 | 1 | 4 | 2 | 8 | 1 | 2 | 2 | 1 | 6
2 | Tender Invited | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
2 | Tender Re invited | _ | 1 | _ | _ | 1 | _ | _ | _ | _ | 0 | _ | _ | 400 | _ | _ | 400 | _ | 407.93 | _ | _ | 407.93 | _ | _ | _ | _ | _
4 | Pending with CE | _ | _ | _ | _ | 0 |  | 0 |  |  |  |  | _ | _ | _ | _ | 0 | _ | _ | _ | _ | 0 | _ | _ | _ | _ | _
3 | Pending with F&CC | _ | _ | 1 | 3 | 4 | [6 empty] | _ | _ | 99.26 | 344.12 | 443.38 | _ | _ | 99.26 | 341.74 | 441 | _ | _ | _ | _ | _
4 | Evaluation of Technical Bid under Process | _ | _ | _ | 1 | 1 | [6 empty] | _ | _ | _ | 700 | 700 | _ | _ | _ | 700 | 700 | _ | _ | _ | _ | _
5 | Financial Bid Opened | 2 | _ | _ | _ | 2 | [6 empty] | 127 | _ | _ | _ | 127 | 127 | _ | _ | _ | 127 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
6 | Case under Process | 2 | _ | 3 | _ | 5 | [6 empty] | 1096.8 | _ | 972.47 | _ | 2069.27 | 1043.14 | _ | 846.43 | _ | 1889.57 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| Total | 16 | 24 | 13 | 16 | 69 | 0 | 0 |  |  | 0 | 0 | 2485.5 | 2914.31 | 2787.26 | 2935.03 | 11122.1 | 2494.44 | 2971.6 | 2154.2 | 2844.04 | 10464.28 | 159.25 | 529.72 | 259.77 | 500.22 | 1448.96 | 10 | 20 | 3 | 9 | 42 | 1 | 1 | 4 | 2 | 8 | 1 | 2 | 2 | 1 | 6