## NCAP Ph-I Zonewise
Summary- NCAP Phase-I (Zonewise)
[22 empty] | (Figure Rs. In Lacs) |  |  | 08.02.2022 | [6 empty] | Detail of works
Sr No. | Description | No. of Works | [5 empty] | E/Cost | [5 empty] | Amended E/Cost Vetted by CE | [5 empty] | Tender Cost | [5 empty] | Financial Progress (Lacs) | [5 empty] | Started | [5 empty] | Not Started | [5 empty] | Completed
|  | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total
1 | Work order Issued | 2 | 1 | 1 | 6 | 2 | 12 | 212.06 | 88.15 | 95.58 | 734.91 | 131 | 1261.7 | 226.27 | 96.86 | 95.58 | 797.92 | 107.67 | 1324.3 | 211.49 | 92.36 | 94.15 | 735.51 | 98.03 | 1231.54 | 8 | 0 | 23.44 | 127.81 | 0 | 159.25 | 2 | 1 | 1 | 4 | 2 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1
2 | Tender invited | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
3 | Tender Reinvited | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
4 | Pending with CE | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
5 | Pending with F&CC | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
6 | Evaluation of Technical Bid Under Process | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
2 | Financial Bid Opened | _ | _ | _ | _ | 2 | 2 | _ | _ | _ | _ | 127 | 127 | _ | _ | _ | _ | 127 | 127 | _ | _ | _ | _ | _ |  | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
3 | Case Under Process | _ | _ | _ | _ | 2 | 2 | _ | _ | _ | _ | 1096.8 | 1096.8 | _ | _ | _ | _ | 1043.14 | 1043.14 | _ | _ | _ | _ | _ |  | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| Total | 2 | 1 | 1 | 6 | 6 | 16 | 212.06 | 88.15 | 95.58 | 734.91 | 1354.8 | 2485.5 | 226.27 | 96.86 | 95.58 | 797.92 | 1277.81 | 2494.44 | 211.49 | 92.36 | 94.15 | 735.51 | 98.03 | 1231.54 | 8 | 0 | 23.44 | 127.81 | 0 | 159.25 | 2 | 1 | 1 | 4 | 2 | 10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1