## SWM Phase I
08.02.2022
Summary
Solid Waste Management Phase-I Works
Sr. No. | Description | No. of Works | E/Cost | Amended E/Cost | T/cost | Financial Progress (Lacs) | No of works
[7 empty] | Started | Not Started | Completed | Total
1 | Work order Issued | 9 | 1715.53 | 1208.51 | 1111.87 | 259.77 | 3 | 4 | 2 | 9
2 | Tender invited | _ | _ | _ | _
3 | Tender invited | _ | _ | _ | _
4 | Pending with CE | _ | _ | _ | _
2 | Pending in F&CC | 1 | 99.26 | 99.26 | 82.2 | _ | _ | _ | _
6 | Evaluation of Technical Bid Under Process | _ | _ | _ | _
7 | Financial Bid Opened | _ | _ | _ | _
3 | Case Under Process | 3 | 972.47 | 846.43 | _ | _ | _ | _ | _
| Total | 13 | 2787.26 | 2154.2 | 1194.07 | 259.77 | 3 | 4 | 2 | 9