## SWM Phase II Zonewise
08.02.2022
Summary NCAP Phase-I
Solid Waste Management Ph-II (Zone-wise)
[25 empty] | (Figure Rs. In Lacs) | [10 empty] | Detail of works
Sr No. | Description | No. of Works | [6 empty] | E/Cost | [6 empty] | Amended E/Cost Vetted by CE | [6 empty] | Tender Cost | [6 empty] | Financial Progress (Lacs) | [5 empty] | Started | [5 empty] | Not Started | [5 empty] | Completed
|  | A | B | C | D | O&M/Workshop | Gen | Total | A | B | C | D | O&M/Workshop | Gen | Total | A | B | C | D | O&M/Workshop | Gen | Total | A | B | C | D | O&M/Workshop | Gen | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total | A | B | C | D | O&M/Workshop | Total
1 | Work order Issued | _ | 3 | _ | 1 | 8 | _ | 12 | _ | 504.24 | _ | 100 | 1286.67 | _ | 1890.91 | _ | 504.24 | _ | 84.09 | 1213.97 | _ | 1802.3 | _ | 511.08 | _ | 76.53 | 1165.07 | _ | 1752.68 | 0 | 19.51 | 0 | 0 | 480.71 | 500.22 | 0 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1
2 | Tender invited | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
3 | Tender RE invited | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
4 | Pending with CE | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
2 | Pending in F&CC | _ |  | _ |  | 3 | _ | 3 | _ |  | _ | _ | 344.12 | _ | 344.12 | _ |  | _ |  | 341.74 | _ | 341.74 | _ | _ | _ | _ | 315.95 | _ | 315.95 | _ | _ | _ | _ | _ | _
3 | Evaluation of Technical Bid Under Process | _ | _ | _ | 1 | _ | _ | 1 | _ | _ | _ | 700 | - | _ | 700 | _ |  | _ | 700 | _ | _ | 700 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
7 | Financial Bid Opened | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | [6 empty] | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
8 | Case Under Process | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | [6 empty] | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| Total |  | 3 |  | 2 | 11 |  | 16 |  | 504.24 |  | 800 | 1630.79 |  | 2935.03 |  | 504.24 |  | 784.09 | 1555.71 |  | 2844.04 |  | 511.08 |  | 76.53 | 1481.02 |  | 2068.63 | 0 | 19.51 | 0 | 0 | 480.71 | 500.22 | 0 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1